## Revised
Draft Project Plan - Recycle Your Electricals
Project development work
| Full project activity roll out | [40 empty] | x | Project deliverable
Project milestone
Operations launch
Comms launch
Project start date
|  | Quarter 1 | [12 empty] | Quarter 2 | [13 empty] | Quarter 3 | [12 empty] | Quarter 4
|  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November
 | time axis 2024-04-01 to 2025-11-24
Task no. | Task description | time axis 2024-04-01 to 2025-11-24
Management and catch ups | Initial meeting with Material Focus
Project management (including update meetings)
Partnership project meetings
Set up | Project set up
Establish marketing and communications plan
Completion of benchmark WEEE data (data reporting)
Completion and return of New Supplier form
Identify community networks, social media, local/sector press
Task 1 | Launch preparation - Operations
Task 2 | Launch preparation - Communications
Submit first draft comms assets for review
Submit first draft press release to MF PR team
MF comms review process - feedback and alterations (need around 4 weeks)
MF PR review process - feedback and alterations (need around 4 weeks)
Comms assets signed off ready for order
Press release signed off ready for issue
Task 3 | Project Launch
Comms Launch
Media launch - Press release issued
Ongoing promotion
Operations launch
Task 4 | Project reporting
Monthly data reporting
Quarterly reporting
Close out | Legacy planning and sharing of learning
Completion of project impact report based on 12 months of learning
Review of systems to embed for longevity
Close out meeting