## Revised
Draft Project Plan - Recycle Your Electricals
The project plan below is to be used as an example - Timeframes will vary between projects according to different partners, suppliers, and project characteristics
Project development work
| Full project activity roll out | [40 empty] | x | Project deliverable
Project milestone
Operations launch
Comms launch
Project start date | April 1st 2024
|  | Quarter 1 | [12 empty] | Quarter 2 | [13 empty] | Quarter 3 | [12 empty] | Quarter 4
|  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August
 | time axis 2024-04-01 to 2025-08-18
Task no. | Task description | time axis 2024-04-01 to 2025-08-18
Management and catch ups | Initial meeting with Material Focus | bar: 2024-04-01
Project management (including update meetings)
Partnership project meetings | bar: 2024-04-01 to 2025-03-10; 2025-03-24 to 2025-03-31; 2025-04-28; 2025-05-26; 2025-06-23; 2025-07-28
Set up | Project set up
Establish marketing and communications plan | bar: 2024-04-01 to 2024-04-15
Completion of benchmark WEEE data (data reporting) | bar: 2024-04-01 to 2024-04-15
Completion and return of New Supplier form | bar: 2024-04-01 to 2024-04-15
Identify community networks, social media, local/sector press | bar: 2024-04-22 to 2024-04-29
Task 1 | Launch preparation - Operations
Identify company to retrofit vehicles with collection cages | bar: 2024-04-22 to 2024-04-29
Retrofitting vehicle fleet with collection cages | bar: 2024-05-06 to 2024-06-03
Send MF the completed spreadsheet so that kerbside service can be added to RYE locator | bar: 2024-05-13
Task 2 | Launch preparation - Communications
Submit first draft comms assets for review | bar: 2024-05-06
Submit first draft press release to MF PR team | bar: 2024-05-06
MF comms review process - feedback and alterations | bar: 2024-05-13 to 2024-06-03
MF PR review process - feedback and alterations | bar: 2024-05-13 to 2024-06-03
Comms assets signed off ready for order | bar: 2024-06-10
Press release signed off ready for issue | bar: 2024-06-10
Task 3 | Project Launch
Comms Launch | bar: 2024-06-24
Leaflet distribution | bar: 2024-06-24 to 2024-07-08
Posters put up | bar: 2024-06-24
Media launch - Press release issued | bar: 2024-07-01
Ongoing social media promotion | bar: 2024-07-08 to 2025-07-07
Operations launch | bar: 2024-07-01
Vehicles collecting electrical goods | bar: 2024-07-01 to 2025-07-07
Task 4 | Project reporting
Monthly data reporting | bar: 2024-08-05; 2024-09-02; 2024-09-30; 2024-10-28; 2024-11-25; 2024-12-23; 2025-01-20; 2025-02-17; 2025-03-17; 2025-04-14; 2025-05-12; 2025-06-09; 2025-06-23
Quarterly reporting | bar: 2024-07-01; 2024-09-23; 2024-12-16; 2025-03-10; 2025-06-02
Close out | Legacy planning and sharing of learning
Completion of project impact report based on 12 months of learning | bar: 2025-07-14 to 2025-07-28
Review of systems to embed for longevity | bar: 2025-07-14 to 2025-07-28
Close out meeting | bar: 2025-07-14