## Revised
Example pilot plan - Recycle Your Electricals
Pilot development work
Full pilot activity roll out
Pilot milestone
Pilot launch date (comms launch)
Pilot end date (1 year from comms launch)
x | Pilot deliverable
|  | Quarter 1 | [12 empty] | Quarter 2 | [12 empty] | Quarter 3 | [12 empty] | Quarter 4
|  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | 2025-09-01 |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May
 | time axis 2025-01-06 to 2026-05-18
Task no. | Task description | time axis 2025-01-06 to 2026-05-18
Management and catch ups | Terms and conditions completed and signed | bar: 2025-01-06
Initial meeting with Material Focus | bar: 2025-01-13
Project management (including update meetings)
Partnership pilot meetings | bar: 2025-01-20; 2025-02-03; 2025-02-17; 2025-03-03
Set up | Pilot set up
Establish marketing and communications plan | bar: 2025-01-20 to 2025-02-17
Completion of benchmark WEEE data (data reporting) | bar: 2025-01-20 to 2025-01-27
Completion and return of New Supplier form | bar: 2025-01-20 to 2025-01-27
Identify community networks, social media, local/sector press | bar: 2025-01-20 to 2025-02-24
Operational launch preparation | Bin order placed | bar: 2025-01-20
Bin sticker design signed off | bar: 2025-01-27 to 2025-02-03
Locations confirmed | bar: 2025-01-27 to 2025-03-03
Bins installed | bar: 2025-02-24 to 2025-03-10
Finalise collections contracts | bar: 2025-01-20 to 2025-02-03; 2025-03-17
Operational launch date
Communications launch preparation | Comms kick off meeting with MF | bar: 2025-01-20
Marketing plan completed | bar: 2025-02-17
Submit brief of assets required to MF | bar: 2025-02-17
Submit first draft press release to MF PR team | bar: 2025-02-17
MF comms review process - feedback and alterations | bar: 2025-02-24 to 2025-03-17
MF PR review process - feedback and alterations | bar: 2025-02-24 to 2025-03-03
Comms assets signed off ready for order | bar: 2025-03-17
Press release signed off ready for issue | bar: 2025-03-17
Mid pilot media release
End of pilot media release
Pilot launch | Communications launch date | bar: 2025-03-24
Media launch - Press release issued | bar: 2025-03-24
Ongoing promotion | bar: 2025-03-24 to 2026-03-16
Pilot reporting | Monthly data reporting | bar: 2025-03-24; 2025-04-21; 2025-05-19; 2025-06-16; 2025-07-14; 2025-08-11; 2025-09-08; 2025-10-06; 2025-11-03; 2025-12-01; 2025-12-29; 2026-01-26; 2026-02-23
Quarterly reporting | bar: 2025-04-07; 2025-06-30; 2025-09-22; 2025-12-15
Mid pilot meeting with Material Focus | bar: 2025-06-30
Invoice and evidence submitted for payment | bar: 2025-04-07; 2025-06-30; 2025-09-22; 2025-12-15; 2026-03-23
Legacy planning and sharing of learning | Completion of pilot impact report based on 12 months of learning | bar: 2026-03-23
Completion of comms impact report | bar: 2026-04-20
Review of systems to embed for longevity | bar: 2026-04-20
End of pilot meeting with Material Focus | bar: 2026-02-23 to 2026-04-20