## Revised
Draft pilot plan - Recycle Your Electricals
Pilot development work
Full pilot activity roll out
Pilot milestone
Pilot launch date (comms launch)
Pilot end date (1 year from comms launch)
x | Pilot deliverable
|  | Quarter 1 | [12 empty] | Quarter 2 | [12 empty] | Quarter 3 | [12 empty] | Quarter 4
|  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May
 | time axis 2025-01-06 to 2026-05-18
Task | Task description | time axis 2025-01-06 to 2026-05-18
Management and catch ups | Terms and conditions completed and signed
Initial meeting with Material Focus
Project management (including update meetings)
Partnership pilot meetings
Set up | Pilot set up
Establish marketing and communications plan
Completion of benchmark WEEE data (data reporting)
Completion and return of New Supplier form
Identify community networks, social media, local/sector press
Operational launch preparation | Bin order placed
Bin sticker design signed off
Locations confirmed
Bins installed
Finalise collections contracts
Operational launch date
Communications launch preparation | Comms kick off meeting with MF
Marketing plan completed
Submit brief of assets required to MF
Submit first draft press release to MF PR team
MF comms review process - feedback and alterations
MF PR review process - feedback and alterations
Comms assets signed off ready for order
Press release signed off ready for issue
Mid pilot media release
End of pilot media release
Pilot launch | Communications launch date
Media launch - Press release issued
Ongoing promotion
Pilot reporting | Monthly data reporting
Quarterly reporting
Mid pilot meeting with Material Focus
Invoice and evidence submitted for payment
Legacy planning and sharing of learning | Completion of pilot impact report based on 12 months of learning
Completion of comms impact report
Review of systems to embed for longevity
End of pilot meeting with Material Focus